## FitPaxPro Tasks
FitPaxPro Developer Tracker
ID | Module | Task | Description | Nupur | Status | Dependency | Priority
FP-001 | Cross-cutting Setup | Module architecture | Set up the folder and namespace conventions for app, module, repository, and swagger files. | Nupur | Not Started | Project bootstrap | High
FP-002 | Cross-cutting Setup | Repository pattern | Create one interface and one repository class for each major feature so business logic stays out of controllers. | Nupur | Not Started | Module architecture | High
FP-003 | Cross-cutting Setup | Route versioning | Group all mobile APIs under a stable prefix like /api/v1 or /api/mobile and keep module routes isolated. | Arvind | Not Started | Module architecture | High
FP-004 | Cross-cutting Setup | Request validation | Add dedicated FormRequest or validator rules for each create and login endpoint. | Arvind | Not Started | Every API endpoint | High
FP-005 | Cross-cutting Setup | Response format | Return a consistent JSON structure with success, message, data, and validation error keys. | Arvind | Not Started | All API endpoints | High
FP-006 | Cross-cutting Setup | File upload helper | Centralize upload paths, file validation, disk selection, and cleanup logic for images and documents. | Arvind | Not Started | Media related features | High
FP-007 | Cross-cutting Setup | Swagger setup | Keep all OpenAPI annotations inside app and Modules so every endpoint is discoverable. | Arvind | Not Started | l5-swagger package | High
FP-008 | Cross-cutting Setup | Test baseline | Create feature tests for the most important happy paths and validation failures. | Arvind | Not Started | API endpoints | High
FP-009 | Cross-cutting Setup | Deployment checklist | Document env vars, cache clear commands, permission requirements, and docs generation command for live servers. | Nupur | Not Started | Production deployment | Medium
FP-010 | Vendor Registration | Vendor schema | Create the vendors table with name, email, phone, password, status, soft deletes, and timestamps. | Nupur | Not Started | Cross-cutting Setup | High
FP-011 | Vendor Registration | Vendor model | Add the Vendor model with fillable fields, casts, relations, and token support if vendors authenticate. | Nupur | Not Started | Vendor schema | High
FP-012 | Vendor Registration | Register API | Build the vendor registration endpoint, validate required fields, and create the vendor record. | Arvind | Not Started | Vendor model | High
FP-013 | Vendor Registration | Login API | Build the vendor login endpoint with email or phone lookup and secure token generation. | Arvind | Not Started | Register API | High
FP-014 | Vendor Registration | Logout and revoke | Add a logout endpoint that revokes the current token or clears the session. | Arvind | Not Started | Login API | Medium
FP-015 | Vendor Registration | Vendor auth docs | Add Swagger annotations for register, login, logout, validation, and success/error responses. | Arvind | Not Started | Register API, Login API | Medium
FP-016 | Gym Profile | Gym table | Create the gyms table with vendor/user links, name, address, contact, timings, latitude, longitude, and approval status. | Nupur | Not Started | Vendor schema | High
FP-017 | Gym Profile | Gym model | Add the Gym model with relations to owner, media, plans, reviews, enquiries, and attendance. | Nupur | Not Started | Gym table | High
FP-018 | Gym Profile | Profile APIs | Build create, read, and update APIs for gym profile data. | Arvind | Not Started | Gym model | High
FP-019 | Gym Profile | Location fields | Validate address, city, state, pincode, and geo coordinates before save. | Arvind | Not Started | Profile APIs | High
FP-020 | Gym Profile | Media upload | Allow gym images, cover photos, and video links or uploads using the shared upload helper. | Arvind | Not Started | File upload helper | High
FP-021 | Gym Profile | Approval workflow | Add active, pending, and rejected flags so admins can approve gym profiles. | Nupur | Not Started | Gym table | Medium
FP-022 | Gym Profile | Gym docs | Document gym profile endpoints, payloads, and response examples in Swagger. | Arvind | Not Started | Profile APIs | Medium
FP-023 | Membership | Plan schema | Create membership plan storage with title, duration, price, features, and visibility. | Nupur | Not Started | Gym table | High
FP-024 | Membership | Plan model | Add the membership plan model and relations to gyms and subscriptions. | Nupur | Not Started | Plan schema | High
FP-025 | Membership | Plan CRUD | Build create, update, list, detail, and delete APIs for membership plans. | Arvind | Not Started | Plan model | High
FP-026 | Membership | Pricing rules | Validate duration, discount, GST, and active dates before saving a plan. | Arvind | Not Started | Plan CRUD | High
FP-027 | Membership | Assign plan | Add an endpoint to assign or subscribe a member to a plan with start and end dates. | Arvind | Not Started | Plan CRUD | High
FP-028 | Membership | Expiry handling | Add logic for expired memberships and plan status changes based on end date. | Nupur | Not Started | Assign plan | Medium
FP-029 | Membership | Membership docs | Add Swagger docs for plan CRUD, assign flow, and validation cases. | Arvind | Not Started | Plan CRUD | Medium
FP-030 | Trainers | Trainer schema | Create trainer profile fields like name, specialization, certifications, experience, availability, and status. | Nupur | Not Started | Gym table | High
FP-031 | Trainers | Trainer model | Add trainer relations to gyms, schedules, reviews, and certification files. | Nupur | Not Started | Trainer schema | High
FP-032 | Trainers | Trainer CRUD | Build APIs to create, update, list, and delete trainer profiles. | Arvind | Not Started | Trainer model | High
FP-033 | Trainers | Certification upload | Allow certificate and profile image upload with file type and size validation. | Arvind | Not Started | File upload helper | High
FP-034 | Trainers | Availability slots | Store working days, time slots, and booking availability per trainer. | Nupur | Not Started | Trainer CRUD | Medium
FP-035 | Trainers | Verification status | Add pending, verified, and rejected states for trainer approval. | Nupur | Not Started | Trainer schema | Medium
FP-036 | Users | User registration | Build the user signup endpoint with validation for name, email, password, phone, and device name. | Arvind | Not Started | Cross-cutting Setup | High
FP-037 | Users | User login/logout | Implement login with token generation and logout with token revocation. | Arvind | Not Started | User registration | High
FP-038 | Users | Profile APIs | Add get profile and update profile endpoints for user data. | Arvind | Not Started | User registration | High
FP-039 | Users | Password reset | Add forgot password and reset password flow if the mobile app requires email or OTP recovery. | Arvind | Not Started | User login/logout | Medium
FP-040 | Users | Device token | Store and refresh the device token used for push notifications. | Arvind | Not Started | User login/logout | Medium
FP-041 | Users | User type mapping | Keep user type and role mapping consistent between mobile users, vendors, trainers, and admins. | Nupur | Not Started | User registration | Medium
FP-042 | Users | User docs | Add Swagger docs for auth, profile, password recovery, and token lifecycle. | Arvind | Not Started | User registration | Medium
FP-043 | Fitness | Workout schema | Create tables for workout plans, workout days, and assigned exercises. | Nupur | Not Started | Exercise DB | High
FP-044 | Fitness | Workout model | Add relations between workout plans, users, gyms, and exercise items. | Nupur | Not Started | Workout schema | High
FP-045 | Fitness | Workout CRUD | Build APIs to create, edit, list, and delete workout plans. | Arvind | Not Started | Workout model | High
FP-046 | Fitness | Plan assignment | Add an endpoint to assign a workout plan to a user or gym member. | Arvind | Not Started | Workout CRUD | High
FP-047 | Fitness | Progress tracking | Store workout completion, reps, sets, and status updates for progress history. | Arvind | Not Started | Plan assignment | Medium
FP-048 | Fitness | Workout docs | Document workout plan, assignment, and progress endpoints in Swagger. | Arvind | Not Started | Workout CRUD | Medium
FP-049 | Exercise DB | Exercise schema | Create the exercise master table with name, category, muscle group, equipment, difficulty, and instructions. | Nupur | Not Started | Cross-cutting Setup | High
FP-050 | Exercise DB | Exercise model | Add model relations for categories, media, and workout plan linking. | Nupur | Not Started | Exercise schema | High
FP-051 | Exercise DB | Filter endpoints | Build search, filter, and pagination APIs for exercise browsing. | Arvind | Not Started | Exercise model | High
FP-052 | Exercise DB | Seed library | Insert a starter exercise library so the app is usable without manual admin entry. | Nupur | Not Started | Exercise schema | Medium
FP-053 | Exercise DB | Exercise docs | Add Swagger docs for browsing, filtering, and exercise details. | Arvind | Not Started | Filter endpoints | Medium
FP-054 | Diet | Meal schema | Create meal log tables for food name, quantity, calories, protein, carbs, fat, and logged time. | Nupur | Not Started | Cross-cutting Setup | High
FP-055 | Diet | Meal model | Add diet entry relations to users, days, and summaries. | Nupur | Not Started | Meal schema | High
FP-056 | Diet | Food logging APIs | Build endpoints for adding, editing, and deleting meals. | Arvind | Not Started | Meal model | High
FP-057 | Diet | Calorie math | Calculate totals for calories and macros per meal and per day. | Arvind | Not Started | Food logging APIs | High
FP-058 | Diet | Meal types | Validate breakfast, lunch, dinner, snacks, and custom entries. | Arvind | Not Started | Food logging APIs | Medium
FP-059 | Diet | Daily summary | Expose a daily diet summary endpoint for the mobile dashboard. | Arvind | Not Started | Calorie math | Medium
FP-060 | Diet | Diet docs | Document diet logging, summaries, and validation errors in Swagger. | Arvind | Not Started | Food logging APIs | Medium
FP-061 | Health Tracking | Metrics schema | Create storage for weight, body fat, BMI, water intake, steps, and other health metrics. | Nupur | Not Started | Cross-cutting Setup | High
FP-062 | Health Tracking | Metrics model | Add the health log model with user relations and casts for numeric fields. | Nupur | Not Started | Metrics schema | High
FP-063 | Health Tracking | Measurement APIs | Build endpoints for adding and updating health measurements. | Arvind | Not Started | Metrics model | High
FP-064 | Health Tracking | Trend dashboard | Return chart-ready history data for the mobile progress dashboard. | Arvind | Not Started | Measurement APIs | High
FP-065 | Health Tracking | Goals and reminders | Store goal targets and reminder flags for weight or hydration tracking. | Nupur | Not Started | Metrics schema | Medium
FP-066 | Health Tracking | Health docs | Add Swagger documentation for metrics entry and dashboard response payloads. | Arvind | Not Started | Measurement APIs | Medium
FP-067 | Community | Feed schema | Create tables for posts, comments, likes, and attachments. | Nupur | Not Started | Cross-cutting Setup | High
FP-068 | Community | Feed model | Add the post model and relations to users, comments, likes, and media. | Nupur | Not Started | Feed schema | High
FP-069 | Community | Post APIs | Build create, update, delete, and list endpoints for the feed. | Arvind | Not Started | Feed model | High
FP-070 | Community | Comments and replies | Add threaded comment and reply endpoints with validation. | Arvind | Not Started | Post APIs | High
FP-071 | Community | Likes and reactions | Add like and unlike endpoints with duplicate protection. | Arvind | Not Started | Post APIs | Medium
FP-072 | Community | Friend or follow flow | Implement friend request or follow request logic depending on the product rules. | Nupur | Not Started | Feed model | Medium
FP-073 | Community | Feed pagination | Return paginated feed data with attached media and author summary fields. | Arvind | Not Started | Post APIs | Medium
FP-074 | Community | Community docs | Document the feed, comments, likes, and request flow in Swagger. | Arvind | Not Started | Post APIs | Medium
FP-075 | Reviews | Review schema | Create the review table with gym, user, rating, comment, status, and timestamps. | Nupur | Not Started | Gym Profile | High
FP-076 | Reviews | Review model | Add relations between reviews, gyms, and users. | Nupur | Not Started | Review schema | High
FP-077 | Reviews | Review APIs | Build endpoints to create, update, list, and delete reviews. | Arvind | Not Started | Review model | High
FP-078 | Reviews | Aggregate rating | Keep average rating and review count updated for each gym. | Nupur | Not Started | Review APIs | Medium
FP-079 | Reviews | Moderation | Add report spam or abuse flow so admins can hide bad reviews. | Nupur | Not Started | Review APIs | Medium
FP-080 | Reviews | Review docs | Add Swagger docs for ratings, comments, and moderation responses. | Arvind | Not Started | Review APIs | Medium
FP-081 | Admin Notifications | FCM token schema | Create storage for device tokens, platform, last used date, and active status. | Nupur | Not Started | User login/logout | High
FP-082 | Admin Notifications | Token sync | Save or refresh the FCM token whenever the mobile app logs in or updates the device. | Arvind | Not Started | FCM token schema | High
FP-083 | Admin Notifications | Push service | Build a reusable notification service for send-to-one and send-to-many push messages. | Nupur | Not Started | Token sync | High
FP-084 | Admin Notifications | Notification log | Store every sent notification with status, payload, and delivery result. | Nupur | Not Started | Push service | High
FP-085 | Admin Notifications | Admin triggers | Trigger notifications from review, inquiry, approval, and membership events. | Nupur | Not Started | Push service | Medium
FP-086 | Admin Notifications | Retry handling | Handle failed notifications with logging and retry-ready status flags. | Nupur | Not Started | Notification log | Medium
FP-087 | Admin Notifications | Notification docs | Document the notification flow and payload examples for the mobile and admin teams. | Nupur | Not Started | Push service | Medium